## Pipeline
Title | Description | New Contract Reference | Value | Value Range (Hide in Reports) | Category | Service | Directorate | PLANNED Advert Dispatch Date | PLANNED Tender Return Date | PLANNED Award Date | PLANNED Contract Start
Property Services Cleaning, Customer Care and Posting of Bus Timetables |  | CA1226 | 2075000.34 | 1M-5M | Facilities Management | Facilities & Assets | Transport Services | 2025-10-14 | 2025-11-14 | 2026-01-02 | 2026-02-01
Mobile voice and data | Mobile voice and data provider as our current contract will come to expire 31st August 2027. This procurement will take 6-9 to implement and then do a transfer of contracts from old supplier to new supplier. | CA62579 | 60000 | 50K-100K | Digital & Technology | Digital & Technology Services | Corporate Centre | 2026-05-01 | 2026-05-29 | 2026-06-10 | 2026-06-17
VAT Professional Services | VAT Consultancy / Professional Services | n/a | 100000 | 100K-500K |  | Finance | Corporate Centre | 2026-05-18 | 2026-06-01 | 2026-06-22 | 2026-06-29
The Careers and Enterprise Grant | West Yorkshire Careers Hub - and partner to deliver in WY the Hub to 180 + secondary schools, colleges and 6th forms | NA | 500000 | 500K-1M |  | Employment & Skills | Inclusive Economy, Skills & Culture | 2026-05-25 | 2026-06-29 | 2026-07-27 | 2026-08-03
M&E Services Contract | M&E Services Contract | CA51855 | 2150000 | 1M-5M | Facilities Management | Facilities & Assets | Transport Services | 2026-06-01 | 2026-07-01 | 2026-09-01 | 2026-10-01
Bus Franchising - Round 3 - Tier C | Procurement of Franchised Bus Services in West Yorkshire - Tier C (15 Lots) . Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 10000000 | 10M-20M | Transport | Bus Reform | Bus Franchising | 2026-07-01 |  | 2027-03-31 | 2028-01-01
Bus Franchising - Round 3 - Tier B | Procurement of Franchised Bus Services in West Yorkshire - Tier B (69 Lots) . Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 15000000 | 10M-20M | Transport | Bus Reform | Bus Franchising | 2026-07-01 |  | 2027-03-31 | 2028-01-01
Bus Franchising - Round 3 - Tier A | Procurement of Franchised Bus Services in West Yorkshire - Tier A (3 Lots) . Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 30000000 | 20M+ | Transport | Bus Reform | Bus Franchising | 2026-07-01 |  | 2027-03-31 | 2028-01-01
Revolving Fund – Fund Manager Procurement | Procurement activity to appoint a Fund Manager for the new revolving fund. |  | 4000000 | 1M-5M | Professional Services | Commercial Development & Investment | Finance & Commercial Services | 2026-08-01 | 2026-09-01 | 2026-11-27 | 2027-02-01
West Yorkshire Annual Business Survey | West Yorkshire Combined Authority has procured a contractor to provide a survey of 1,000-1,500 businesses across the West Yorkshire area. | 110001 (66535) | 220000 | 100K-500K | Professional Services | Research & Intelligence | Strategy, Comms. & Intelligence | 2026-09-14 | 2026-10-12 | 2026-12-02 | 2026-12-16
Policy Explorer Tool | We would like to procure a consultant to develop a Policy Explorer Tool that can help the CA rapidly assess a range (and combination of) high level policy / infrastructure interventions at a granular level, to inform the delivery of the Local Transport Plan and the assessment of a range of policy interventions. |  | 100000 | 100K-500K | Built Environment | Transport Policy | Transport Capital Programme | 2027-01-01 | 2027-02-01 | 2027-04-01 | 2027-05-01
Maintenance and Repair of On-street Infrastructure | Provision of on-street new infrastructure which will include new shelters and bus stops, in addition to ongoing maintenance and repair works to existing stock consisting of circa 4,000 shelters and 10,000 bus stops. | CA53197 | 10000000 | 10M-20M | Facilities Management | Facilities & Assets | Transport Services | 2027-01-03 | 2027-02-02 | 2027-04-03 | 2027-05-03
Social Value Management Software | Platform to manage, record, and report on social value delivered on contracts awarded by WYCA |  | 120000 | 100K-500K | Digital & Technology | Commercial | Corporate Centre | 2027-04-01 | 2027-05-01 | 2027-06-30 | 2027-07-30
SEN Taxis DPS | Dynamic Purchasing System for procurement of annual SEN Taxi provision in Wakefield. Current DPS Ref 64800. |  | 28000000 | 20M+ | Transport | Mobility Services | Transport Services | 2027-04-01 | 2027-05-01 | 2027-06-30 | 2027-07-30
SEN Taxis Annual DPS Call-off (2027) | Annual procurement of SEN taxi provision in Wakefield (1 year contracts) DPS Ref 64800. |  | 4000000 | 1M-5M | Transport | Mobility Services | Transport Services | 2027-06-12 | 2027-06-26 | 2027-07-17 | 2027-09-02
Evaluation Services Framework (extension) | Review extension options of Evaluation Services Framework - decide to extend, expire or re-procure. |  | 6500000 | 5M-10M | Professional Services | Research & Intelligence | Strategy, Comms. & Intelligence | 2027-06-28 | 2027-07-14 | 2027-09-08 | 2027-10-28
Portfolio Management & Appraisal Services Framework | qualified and experienced consultant/s to provide advice and support in the appraisal and assurance of scheme project business cases that progress through its local Assurance Framework. Consultants seeking to be appointed to this commission will be expected to demonstrate a breadth of skills and expertise which reflects the broad range of projects that come forward to the Combined Authority for funding, including transport, housing, regeneration, economic development, and flood resilience. | 72922 | 800000 | 500K-1M | Professional Services | Strategic Portfolio Office | Strategy, Comms. & Intelligence | 2027-08-01 | 2027-09-01 | 2027-11-01 | 2027-12-01
Mass Transit Delivery Packages | Mass Transit Construction | N/A | 2500000000 | 20M+ | Built Environment | Mass Transit | Mass Transit | 2028-01-01 |  |  | 2029-01-01
Mass Transit and Bus Reform Funding and Finance Partner 2 | Financial support for MT and BR programmes |  | 7000000 | 5M-10M | Services | Finance | Finance & Commercial Services | 2028-03-31 | 2028-04-30 | 2028-06-29 | 2028-07-29
Better Homes Hub - Retrofit One Stop Shop | Better Homes Hub - Retrofit One Stop Shop |  | 20000000 | 20M+ | Built Environment | Home Energy West Yorkshire | Policing, Environment & Place | 2029-12-01 | 2030-02-01 | 2030-04-01 | 2030-06-01
TCF Monitoring - AI mode Counter Procurement | Supply and install 30 AI traffic counters across the five districts of West Yorkshire, with 5 years maintenance and support. Further counter may be procured within the 5 year period where required. | 51317 | 450000 | 100K-500K | Professional Services | Research & Intelligence | Strategy, Comms. & Intelligence | 2031-07-01 | 2031-08-01 | 2031-10-01 | 2031-11-01
Real Time Information System | Provision of an Advanced Yorkshire & Humber Real Time Information System and associated services to the Combined Authority (the Services) | PROJECT CA1429 | 5000000 | 5M-10M | Digital & Technology | Digital & Technology Services | Corporate Centre | 2031-09-01 | 2031-10-01 | 2031-12-01 | 2032-01-01
Insurance Brokerage Services | Insurance brokerage services for the Combined Authority | 87456 | 60000 | 50K-100K |  | Legal & Governance
Behaviour Change Evaluation | Further competition through the evaluation services framework to procure an evaluation of the behaviour change programme |  | 75000 | 50K-100K |  | Research & Intelligence | Strategy, Comms & Intelligence |  |  |  | 2026-11-30
Re-procurement of 365Respone Flexiroute system | Re-procurement of 365Respone Flexiroute system | 89529 | 200000 | 100K-500K | Digital & Technology | Digital & Technology Services | Corporate Centre
Wakefield Bus Station day one refurb | Refurb, improvement and maintenance type works including roof repairs, toilet refurbs, masonary work and heating and ventilation works |  | 400000 | 100K-500K |  | Transport Implementation | Transport Capital Programme |  |  |  | 2026-09-01
Maintenance Contract for CCTV across West Yorkshire Combined Authority Property | Procurement for the provision of fibre optic circuits for WYCA CCTV System. | 87865 | 400000 | 100K-500K | Transport | Transport Implementation | Transport Policy & Delivery
Housing Enabler Fund | We are looking for a property consultant to provide project specific support in helping sites on the West Yorkshire Housing Pipeline to be de-risked for housing development. This includes technical advice/support, local level support with project management/planning, support for LA planning teams and CA intelligence building regarding site scoping and development parameters. |  | 500000 | 500K-1M |  | Place & Environment Policy | Policing, Environment & Place |  |  |  | 2027-06-01
Mass Transit Planning Consultancy | Planning support for Mass Transit early works |  | 1500000 | 1M-5M |  | Mass Transit | Mass Transit |  |  |  | 2027-02-01
Project Development/Technical Support | Project development and technical assistance support services |  | 1500000 | 1M-5M |  | Place & Environment Policy | Policing, Environment & Place |  |  |  | 2027-06-01
Restorative Justice Service In West Yorkshire | To provide a West Yorkshire wide victim-focused Restorative Justice service that empowers victims of crime by giving them the opportunity to communicate with the person responsible. | 82782 | 2084348 | 1M-5M | Professional Services | Place & Environment Policy | Policing, Environment & Place
Legal Consultant for Housing & Regeneration Programmes | To procure Legal advice for Housing / Regeneration programmes. | 95770 | 3000000 | 1M-5M | Professional Services | Regeneration | Policing, Environment & Place |  |  |  | 2026-10-01
Commercial Consultant for Housing & Regeneration Programmes | A consultant partner has been appointed to support the Combined Authority in driving focused activity across a range of funds and projects. The appointed supplier will provide expertise and capacity to ensure Housing and Regeneration programmes are delivered effectively and at pace. | 95769 | 3500000 | 1M-5M | Professional Services | Regeneration | Policing, Environment & Place
Estate Management and Valuation Services Contract | provide an estate management service relating to portfolio of properties, land and assets and located in the five districts of West Yorkshire | 92148 | 4000000 | 1M-5M | Built Environment | Facilities & Assets | Transport Services
Mass Transit - Land & Property Partner 2 (LPP2) Contract | Under the Land and Property Partner (LPP) contract between WYCA and Arcadis, Arcadis is responsible for leading the delivery of land and property services required to support the West Yorkshire Mass Transit Programme. Arcadis is supported by specialist subcontractor Ardent, who brings additional technical expertise in land referencing and compulsory acquisition. The services being delivered by Arcadis (with support from Ardent) include: • Land Referencing: Identification and verification of land ownership, occupiers, and legal interests impacted by the proposed mass transit infrastructure, including routes, depots, and Park & Ride sites. • Book of Reference and Land Plans: Preparation of the statutory documentation necessary to support any Transport and Works Act Order (TWAO) or Compulsory Purchase Order (CPO), ensuring compliance with legal requirements and accuracy of data. • Compulsory Purchase and Compensation Support: Development of land acquisition strategies and provision of technical advice on compensation, valuations, and negotiations with affected landowners and occupiers. • Policy Development: Supporting WYCA in the creation and refinement of land and property policies, including approaches to compensation, acquisition, landowner engagement, and objection management, to ensure alignment with programme objectives, best practice, and statutory frameworks. • Stakeholder Engagement Support: Supporting WYCA in engagement with landowners and other parties with legal interests to foster transparency, address concerns, and minimise objections during the statutory process. • Legal and Procedural Compliance: Ensuring all land-related activities are compliant with relevant legislation and regulations, including the Transport and Works Act, the Planning Act, and equality and environmental obligations. These services are essential to securing land rights, supporting statutory approvals, and ensuring the successful and timely delivery of the West Yorkshire Mass Transit Programme. |  | 6500000 | 5M-10M | Professional Services | Mass Transit | Mass Transit |  |  |  | 2026-12-01
Mass Transit Environmental Partner 2 | Environmental Partner to support the ongoing Mass Transit Programme | 87599 | 7500000 | 5M-10M | Professional Services | Mass Transit | Mass Transit |  |  |  | 2026-12-01
Mass Transit Independent Competent Person | Appoint an 'independent competent person' (ICP) to help devise a written scheme of verification for the Mass Transit system in compliance with statutory requirements |  | 8000000 | 5M-10M | Professional Services | Mass Transit | Mass Transit |  |  |  | 2026-10-01
WY Victims Referral, Assessment and Local Support Services | Referral, Assessment and Local Support Services for WY | 98478 | 8400000 | 5M-10M | Professional Services | Place & Environment Policy | Policing, Environment & Place
West Yorkshire Energy Fund - Fund Manger | Fund manager services - DO NOT PUBLISH UNTIL SOC APPROVAL (Jan 27) |  | 9400000 | 5M-10M |  | Place & Environment Policy | Policing, Environment & Place |  |  |  | 2028-06-05
Electricity Supply | Electricity Supply |  | 10000000 | 10M-20M | Facilities Management | Facilities & Assets | Transport Services |  |  |  | 2028-04-01
Bradford Bus Station | We are in the early stages of a scheme looking at new bus station infrastructure in Bradford so likely there will be a number of procurement exercises coming up for this to add to the pipeline. We are going to need business case support for SOC, OBC and FBC and likely some Design & Network Planning work to support the optioneering exercises (though this is also being looked into by the mass transit team so may sit with them, tbc). Then we will need to procure a designer and eventually contractors for construction. | n/a | 35000000 | 20M+ | Built Environment | Transport Implementation | Transport Capital Programme |  |  |  | 2029-01-01
Bus Depot - Electrical Vehicle Infrastructure Upgrades | We are looking for a turn key contractor to upgrade bus depots (once they are owned by the CA) to install Electric Vehicle Infrastructure for the new Zero Emission Buses which are due to be rolled out as part of Franchising/Bus Reform. This will involve full design work, upgrades to the grid, installation of infrastructure. | 103169 | 82000000 | 20M+ | Transport | Bus Reform | Bus Franchising |  |  |  | 2028-02-01

## WIP
Title | Description | New Contract Reference | Value | Value Range (Hide in Reports) | Category | Service | Directorate | PLANNED Advert Dispatch Date | PLANNED Tender Return Date | PLANNED Award Date | PLANNED Contract Start | ACTUAL Advert Dispatch Date | ACTUAL Tender Return Date | ACTUAL Award Date | ACTUAL Contract Start
WYBGH: Toolkit development | We are looking to procure a provider to undertake some development activity for the WYBGH toolkit: https://wytoolkit.co.uk/ | N.A | 110000 | 100K-500K | Professional Services | Business Innovation Skills & Culture Policy | Inclusive Economy, Skills & Culture | 2027-01-08 | 2026-02-08 | 2027-03-08 | 2027-04-08
Home Energy West Yorkshire low interest loan (phase 2) | Partner to support the operation and management of a low interest loan pot for residential efficiency development |  | 8500000 | 5M-10M | Professional Services | Place & Environment Policy | Policing, Environment & Place | 2026-01-13 | 2026-02-13 | 2026-04-13 | 2026-05-13
CityConnect Programme Evaluation | Primary and secondary data collection, including surveys, pedestrian and cyclist counts, and air quality monitoring. Includes independent analysis and reporting on programme outcomes and impacts. Work will align with HM Treasury’s Magenta Book and incorporate policy contribution and theory of change development. |  | 100000 | 100K-500K | Professional Services | Research & Intelligence | Strategy, Comms. & Intelligence | 2026-02-01 | 2026-03-01 | 2026-05-01 | 2026-05-02
Bus Franchising - Round 1 - Tier B | Procurement of Franchised Bus Services in West Yorkshire - Tier B (11 Lots) . Service details, value and procurement process remain subject to finalisation prior to procurement commencement. | 104505 | 31000000 | 20M+ | Transport | Bus Reform | Bus Franchising | 2025-10-20 | 2026-03-25 | 2026-08-01 | 2026-08-16 | 2025-10-20
Bus Franchising - Round 1 - Tier C | Procurement of Franchised Bus Services in West Yorkshire - Tier C (15 Lots) . Service details, value and procurement process remain subject to finalisation prior to procurement commencement. | 104510 | 19000000 | 10M-20M | Transport | Bus Reform | Bus Franchising | 2025-10-20 | 2026-04-03 | 2026-08-01 | 2026-08-16 | 2025-10-20
Bus Franchising - Round 1 - Tier A | Procurement of Franchised Bus Services in West Yorkshire - Tier A (3 Lots) . Service details, value and procurement process remain subject to finalisation prior to procurement commencement. | 104117 | 70000000 | 20M+ | Transport | Bus Reform | Bus Franchising | 2025-10-06 | 2026-04-15 | 2026-08-01 | 2026-08-16 | 2025-10-07
​Service Design and Implementation Budget: Customer Workstream | A three phase programme of works in the customer workstream for Bus Franchising. Phase 1 will be a re evaluation of the workstream through the lens of MVP, Phase 2 will be developing the accepted MVP to a day 1 offer and Phase 3 will be moving the MVP through an agile framework towards an optimal end state solution | N/A | 800000 | 500K-1M |  | Bus Reform | Bus Franchising |  | 2026-05-01 | 2026-05-08 | 2026-05-22
Transport Accessibility Tool | To procure a new software licence following the expiry of the basemap TRACC licence in June 2026. | CA49132 | 60000 | 50K-100K | Transport | Research & Intelligence | Strategy, Comms. & Intelligence | 2026-04-29 | 2026-05-27 | 2026-06-17 | 2026-07-01
Ecological Support for Biodiversity Net Gain | Ecological support for BNG delivery, including calling off various tasks such as monitoring reports, spot checks etc. | 99304 | 100000 | 100K-500K | Professional Services | Place & Environment Policy | Policing, Environment & Place | 2026-04-28 | 2026-05-28 | 2026-08-28 | 2026-08-28
Home Energy West Yorkshire - strategic marketing campaign | Development and delivery of a strategic marketing campaign to promote the Home Energy West Yorkshire advice service |  | 200000 | 100K-500K |  | Home Energy West Yorkshire | Policing, Environment & Place | 2026-05-18 | 2026-06-01 | 2026-06-22 | 2026-06-29
Further Education Industry Partnerships Pilot | Research, design and delivery of a pilot programme matching employers/industry with further education (FE) providers to support delivery of teaching. Project design and development, stakeholder liaison and brokerage, project delivery management and monitoring | NA | 160000 | 100K-500K | Professional Services | Employment & Skills | Inclusive Economy, Skills & Culture | 2026-05-02 | 2026-06-02 | 2026-08-02 | 2026-08-15
Customer Contact Centre -Telephony/CRM | To replace the current contract with Redcentric which expires November 2027 - the previous implementation took 1 year therefore we would like to start this in Spring 2026. There is scope for this to change as this service is being considered by Mass Transit/Bus Reform/Fire Service and we need to ensure we are including scope to increase licences as we grow. | CA49137 | 300000 | 100K-500K | Digital & Technology | Bus Reform | Bus Franchising | 2026-06-01 | 2026-07-15 | 2026-11-01 | 2026-12-01
West Yorkshire Perpetrator Contract | The programme will focus on first time, standard level perpetrators of domestic abuse who receive a conditional caution. The programme will be open to those perpetrators aged over 16 only. The successful provider must enable programme access to perpetrators across West Yorkshire. |  | 1750000 | 1M-5M | Professional Services | Policing & Crime | Policing, Environment & Place | 2026-06-11 | 2026-07-17 | 2026-10-08 | 2027-04-01
Supply & support for network infrastructure | Supply & support for network infrastructure | 11022 |  |  | Digital & Technology | Digital & Technology Services | Corporate Centre | 2026-06-16 | 2026-07-24 | 2026-09-10 | 2026-12-01
Bus Franchising Client Side Expert Advice | With just over a year to go before the first round of franchising, we are looking for call-off support from experienced individual(s) who can offer a critical friend role to the Programme Director and SRO. To secure franchising expertise from individuals who have had direct experience of delivering a bus franchising scheme in the UK. This requires the services from appropriately experienced professionals with extensive experience of client-side bus franchising delivery at a senior level. | N/A | 100000 | 100K-500K |  | Bus Reform | Bus Franchising | 2026-06-26 | 2026-07-26 | 2026-06-01 | 2026-07-01
Electric Car Sacrifice Scheme | Seeking to procure a firm to provide an electric car scheme through salary sacrifice to employees as part of the employee reward offer. | 108039 | 0 | 30K-50K | Professional Services | HR | Corporate Centre | 2026-07-28 | 2026-08-11 | 2026-10-01 | 2026-10-15
Food and Drinks Vending Provision | The Combined Authority have appointed a provider for the provision, installation, maintenance and de-installation of snacks and soft drink vending machines at our bus stations/sites. | 110322 | 0 | 30K-50K | Built Environment | Passenger Experience | Transport Services | 2026-07-22 | 2026-08-18 | 2026-09-16 | 2026-09-28 | 2026-09-11
Marketing & Communications Framework (re-tender) | Provision of Marketing and Communications Services | 56970 - Previous | 14000000 | 10M-20M | Communications | Marketing & Campaigns | Strategy, Comms. & Intelligence | 2026-07-11 | 2026-08-21 | 2026-09-24 | 2026-10-01
Cycle to Work Scheme | Arrangements for the WYCA Cycle to Work scheme | 111525 (1307 - Current ) | 90000 | 50K-100K | Professional Services | Finance | Finance & Commercial Services | 2026-08-14 | 2026-08-28 | 2026-10-23 | 2026-10-30
Due Diligence Partner | Procurement of external expertise to perform enhanced and forensic due diligence checks, supplementing internal capabilities | 111194 | 400000 | 100K-500K | Professional Services | Commercial | Finance & Commercial Services | 2026-07-31 | 2026-08-28 | 2026-09-29 | 2026-09-30
Langthwaite Enterprise Zone - Phase 2 DMC Contractor | Support is required for Langthwaite Phase 2 with developing the options and advice is needed in terms of identifying the preferred way forward. The tasks envisaged are: - Support with Pre Market Engagement - Support with procuring a utilities expert to provide advice on what options there are for bringing in connection to the site. - General guidance and support as necessaryA Design and Build Contractor (D&B Contractor) who will be responsible for the design and physical construction of the proposed commercial units. | N/A | 1270000 | 1M-5M |  | Regeneration | Policing, Environment & Place | 2026-08-01 | 2026-09-01 | 2026-11-01 | 2026-12-01
Regional Supported Housing Needs Assessment | Co-commissioning of supported housing needs assessments with the local authorities in accordance with the Supported Housing (Regulatory Oversight) Act 2023 and associated government guidance, with the ability to aggregate the data for West Yorkshire as a whole. | 114109 | 90000 | 50K-100K |  | Place & Environment Policy | Policing, Environment & Place | 2026-08-04 | 2026-09-04 | 2026-10-15 | 2026-11-02
Staff training requirements- L&D Framework | E-Learning modules | 100108417 | 3000000 | 1M-5M | Learning & Development | HR | Corporate Centre | 2026-08-18 | 2026-10-01 | 2027-01-04 | 2027-01-18
Travel Diary Survey for West Yorkshire | The Travel Diary Survey is to collect detailed, qualitative, and quantitative data on the travel experiences of representative residents of West Yorkshire. | 112757 | 300000 | 100K-500K | Professional Services | Research & Intelligence | Strategy, Comms. & Intelligence | 2026-09-04 | 2026-10-02 | 2026-11-27 | 2026-12-04
Temporary Staffing and Hard to Fill Recruitment Vacancies | A programme to support people who have health conditions or disabilities, into work. | 100108419 | 3000000 | 1M-5M | Professional Services | HR | Corporate Centre | 2026-09-01 | 2026-10-15 | 2027-01-01 | 2027-02-01
Lot 1 Crew Rooms Procurement | Fit out of 3 units for Crew rooms in Huddersfield Bus Station, Dewsbury Bus Station and the Headrow. Currently we are exploring the possibility of a three quote for the Headrow and using Willmott Dixon for Dewsbury. But we are likely to require going out to tender for Huddersfield. | 111420 | 611000 | 500K-1M | Built Environment | Bus Reform | Bus Franchising | 2026-09-24 | 2026-10-21 | 2026-12-01 | 2026-12-07
Bus Reform Baseline | Using the Evaluation Services Framework we are looking to commission a supplier to carry out a baseline for the Bus Reform Programme. This will involve conducting primary data collection and synthesis of available secondary data. The exact split of primary and secondary data is still to be determined. | 111422 | 500000 | 500K-1M |  | Research & Intelligence | Strategy, Comms & Intelligence | 2026-10-06 | 2026-10-23 | 2026-11-24 | 2026-12-01
Wakefield Bus Depot | Procurement strategy for design and build, and possibly own, operate and transfer |  | 30000000 | 20M+ | Built Environment | Bus Reform | Transport Capital Programme | 2026-10-15 | 2026-11-01 | 2027-01-01 | 2027-01-01
Healthy Working Life marketing support | To deliver paid marketing campaigns that creates behaviour change, raises awareness and directs employers and individuals to resources, information and support that helps them with health-related employment support. This procurement needs to be delivered and paid by 31st March 2027 |  | 150000 | 100K-500K | Professional Services | Employment & Skills | Inclusive Economy, Skills & Culture | 2026-10-12 | 2026-11-09 | 2026-11-23 | 2026-12-07
Tutor Shortages - Recruitment Campaign | We are looking to procure a supplier to run a marketing campaign to get industry professionals from the Engineering and Manufacturing sector into teaching jobs. The Combined Authority proposes to appoint a specialist supplier to undertake audience research, develop the campaign brand and messaging, create campaign assets and deliver the wider communications and engagement activity. The appointed supplier could also support event planning, stakeholder engagement, marketing activity and campaign evaluation. |  | 90000 | 50K-100K | Professional Services | Employment & Skills | Inclusive Economy, Skills & Culture | 2026-10-13 | 2026-11-10 | 2026-11-24 | 2026-12-08
Bus Franchising - Round 2 - Tier C | Procurement of Franchised Bus Services in West Yorkshire - Tier C (14 Lots) . Service details, value and procurement process remain subject to finalisation prior to procurement commencement. | 112027 | 15464000 | 10M-20M | Transport | Bus Reform | Bus Franchising | 2026-10-19 | 2026-11-20 | 2027-04-12 | 2027-04-29
Bus Franchising - Round 2 - Tier B | Procurement of Franchised Bus Services in West Yorkshire - Tier B (8 Lots) . Service details, value and procurement process remain subject to finalisation prior to procurement commencement. | 112026 | 44835000 | 20M+ | Transport | Bus Reform | Bus Franchising | 2026-10-19 | 2026-11-20 | 2027-04-12 | 2027-04-29
Bus Franchising - Round 2 - Tier A | Procurement of Franchised Bus Services in West Yorkshire - Tier A (2 Lots) . Service details, value and procurement process remain subject to finalisation prior to procurement commencement. | 112025 | 246600000 | 20M+ | Transport | Bus Reform | Bus Franchising | 2026-10-19 | 2026-11-20 | 2027-04-12 | 2027-04-29
Support Services for Regional Domestic Retrofit Programme | The purpose of the commission was to appoint a consultant to work alongside the Combined Authority in developing the Better Homes Hub, a programme to scale-up domestic retrofit in the region that supports and adds value to the work of the five Local Authority’s, West Yorkshire Housing Partnership and other key stakeholders, building on existing activity and funding. | 73729 | 700000 | 500K-1M | Services | Place & Environment Policy | Policing, Environment & Place | 2026-11-01 | 2026-12-01 | 2027-02-04 | 2027-03-04
Appropriate Adult Service for Vulnerable Adults in Custody | A West Yorkshire wide Appropriate Adult Service to Vulnerable Adults in custody in line with the Police & Criminal Evidence Act 1984 (PACE) and other relevant legislation. The ambition of for the service to primarily be delivered by volunteers. | 114594 | 1260000 | 1M-5M | Services | Policing & Crime | Policing, Environment & Place | 2026-11-03 | 2026-12-01 | 2027-02-24 | 2027-03-24
Employment Land Accelerator Professional Services | The Combined Authority requires a broad range of support to help progress employment sites to an investible position. This includes strategic and technical input such as masterplanning, planning, feasibility and viability work, alongside site investigations and market analysis to build a robust evidence base. The role also involves leading stakeholder engagement with landowners, developers and investors, as well as supporting land assembly, valuations and commercial negotiations. Expertise will be needed to advise on delivery models, developer procurement, partnership structures and site disposals, alongside potential Compulsory Purchase Order (CPO) processes. In addition, the consultant will provide client-side support to build local authority capability, manage projects, risks and budgets, and assist with funding bids and governance processes, including reporting and ongoing strategic advice. (the full spec is available in the original ITT) |  | 1400000 | 1M-5M | Professional Services | Place & Environment Policy | Policing, Environment & Place | 2026-11-01 | 2026-12-01 | 2027-01-15 | 2027-02-01
User Centred Design for WY Youth Unemployment Pilot | Through developing and delivering a systematic User Centred Design approach, complemented by a wider range of innovative techniques to drive system redesign, the appointed consultant will lead on the co-design of a Youth Participation System to prevent youth unemployment across West Yorkshire, with implementation of the system beginning in 2027/28 | N/A | 150000 | 100K-500K | Professional Services | Strategy & Corporate Performance | Strategy, Comms & Intelligence | 2026-11-06 | 2026-12-04 | 2027-01-11 | 2027-02-15
West Yorkshire Energy Fund - Consultancy support | Consultancy support for OBC/FBC development |  | 150000 | 100K-500K | Professional Services | Place & Environment Policy | Policing, Environment & Place | 2026-11-12 | 2026-12-10 | 2027-02-04 | 2027-03-01
Langthwaite Enterprise Zone - Phase 2 D&B Contractor | A Design and Build Contractor (D&B Contractor) who will be responsible for the design and physical construction of the proposed commercial units. | N/A | 30000000 | 20M+ | Built Environment | Regeneration | Policing, Environment & Place | 2027-01-01 | 2027-01-31 | 2027-04-01 | 2027-05-01
UKReiiF 2027 West Yorkshire Pavilion | Specialist support, design ,build and take down of the West Yorkshire Pavilion for UKREiiF 2027 |  | 80000 | 50K-100K |  | Marketing & Campaigns | Strategy, Comms & Intelligence |  |  |  | 2026-11-27
Evaluation Strategy Refresh | Evaluation consultancy - mini-competition via the Evaluation Services Framework | 114184 | 80000 | 50K-100K | Professional Services | Research & Intelligence | Strategy, Comms & Intelligence |  |  |  | 2026-09-25
Third Party Land to store the new fleet | Mobile Chargers, Portacabins and Remedial work to prepare land |  | 100000 | 100K-500K |  | Bus Reform | Bus Franchising
Technical Resource Efficiency Audits for businesses | Looking to procure multiple (up to a max of 5) suppliers to sit on a framework to deliver Technical Resource Efficiency Audits for businesses to support and advise on energy efficiency and decarbonisation projects within their businesses premises | 64885 | 100000 | 100K-500K | Professional Services | Business Innovation Skills & Culture Policy | Inclusive Economy, Skills & Culture |  |  |  | 2026-10-01
Quarterly Economic Survey - Leading Indicator Intelligence | The West Yorkshire Combined Authority wishes to procure a quarterly indicator survey of business intelligence to provide timely insight on business confidence and performance across the Leeds City Region. | 58982 - Current | 112000 | 100K-500K | Professional Services | Research & Intelligence | Strategy, Comms. & Intelligence
Stakeholder management system | Tractivity system for Stakeholder Management |  | 148485 | 100K-500K | Digital & Technology | Marketing & Campaigns | Strategy, Comms. & Intelligence |  |  |  | 2026-10-08
Aspiring Pathways Project | The procurement will be for a service provider to deliver a programme of work to support young people in Alternative Provision to learn about work, have experiences of the work place and gain important skills and knowledge to enable them to progress into work. |  | 150000 | 100K-500K | Professional Services | Employment & Skills | Inclusive Economy, Skills & Culture |  |  |  | 2026-09-01
Lost Property | Lost Property system for Bus Franchising |  | 150000 | 100K-500K | Services
Annual Conversation 2026 - Evaluation of Transport FS | Progress plus evaluation for the Annual Conversation, covering multiple schemes grouped together. | 108277 | 153000 | 100K-500K | Professional Services | Research & Intelligence | Strategy, Comms & Intelligence |  |  |  | 2026-06-01
Security Operations Centre (SOC) Extension | Contract Extension | CL01 Cloud Infrastrcture -SOC | 170000 | 100K-500K | Professional Services | Digital & Technology Services | Corporate Centre
Water Utilities (Framework - YPO - Utilities Water – 1008) | The Combined Authority’s current call off contract with Wave via YPOs Water Utilities framework | 68204 | 200000 | #REF! | Facilities Management | Facilities & Assets | Transport Services
Re-procurement of 365Respone Flexiroute system | Re-procurement of 365Respone Flexiroute system | 89529 | 200000 | 100K-500K | Digital & Technology | Digital & Technology Services | Corporate Centre
EAMS - System Solution |  | 113764 | 220000 | 100K-500K | Digital & Technology | Bus Reform | Bus Franchising
Programme process evaluation of the WY Investment Zone | Evaluation services from a contractor on the Evaluation Services Framework | N/A | 250000 | 100K-500K | Professional Services | Place & Environment Policy | Policing, Environment & Place |  |  |  | 2027-03-31
Vehicle disposal/auction supplier | Procurement for supplier to auction/sell/recycle/dipose vehicles that are no longer needed as part of the AccessBus Fleet owned by the CA (which new vehicles are currently being re-procured for). Extension options may be included for disposals of fleet further in the future, particularly given the CA will be owning much more Fleet in future as part of Bus Franchising. |  | 250000 | 100K-500K | Fleet
Leeds Bus Station Roof - NEC PM & Technical Support | Related procurement: 93408 | 108792 | 300000 | 100K-500K |  | Transport Implementation | Transport Capital Programme
Creative Investment Accelerator Programme | Business support, events management, investor networking and introductions, bursary fund administration |  | 300000 | 100K-500K | Professional Services | Business Innovation Skills & Culture Policy | Inclusive Economy, Skills & Culture |  |  |  | 2026-09-01
Payment provider | Card payment provider |  | 450000 | 100K-500K | Transport | Passenger Experience | Transport Services
Alternative Business Models | A supplier(s) to deliver a business support programme that raises awareness of and increases the number of alternative businesses in West Yorkshire. |  | 500000 | 500K-1M | Professional Services | Business Innovation Skills & Culture Policy | Inclusive Economy, Skills & Culture |  |  |  | 2027-01-04
Control Centre IMS |  |  | 600000 | 500K-1M | Digital & Technology | Bus Reform | Bus Franchising
Weaver branded uniform for operators of the WY Bus Network | Weaver branded uniform for operators of the WY Bus Network - all bus stations, drivers, potentionally security staff |  | 1000000 | 1M-5M | Fleet | Bus Reform | Bus Franchising
Development of a Regional Planning Policy Document (Spatial Development Strategy) for West Yorkshire | Consultancy support to develop technical evidence including: Strategic Housing Market Assessment Strategic Green Belt Review Sustainability Appraisal Habitat Regulations Assessment Health Impact Assessment |  | 1500000 | 1M-5M |  | Place & Environment Policy | Policing, Environment & Place |  |  |  | 2027-02-01
West Yorkshire Export Support Programme | Full Description: We are seeking to procure a delivery partner to design and deliver the West Yorkshire Export Support Programme, to help SMEs increase export capability, access new international markets, and grow international sales. The programme will provide a combination of one-to-one export advice, market intelligence, trade mission support, grants, peer networks, and targeted support for priority sectors and underrepresented businesses. The programme aims to increase exports, productivity, business growth, job creation, and West Yorkshire's international competitiveness. |  | 1800000 | 1M-5M | Professional Services | Business Innovation Skills & Culture Policy | Inclusive Economy, Skills & Culture
West Yorkshire Supply Chain Programme | Procure a Delivery Partner to design and deliver the West Yorkshire Supply Chain Programme at a cost of £2,000,000, funded through the Integrated Settlement (April 2026–March 2029). The Partner will deliver a comprehensive programme of SME support, including diagnostics, workshops, OEM/Prime engagement, sector specific masterclasses, and a grant fund, to strengthen supply chain resilience, competitiveness, innovation, and diversification across West Yorkshire’s priority sectors. |  | 2000000 | 1M-5M | Learning & Development | Trade & Investment | Inclusive Economy, Skills & Culture |  |  |  | 2026-09-01
Advertising and Sponsorship Contract | Procurement for Advertising to include on bus, outdoor and shelter advertise aswell as other CA Assets |  | 2000000 | 1M-5M | Transport | Digital & Technology Services | Bus Franchising
Wakefield Bus Depot – NEC Site Supervisor | The Project requires an NEC Site Supervisor to manage quality, monitor site progress, and ensure compliance with the project during construction. |  | 2000000 | 1M-5M | Built Environment | Bus Reform | Transport Capital Programme
Careers Improvement System | The Careers Improvement Service will provide the primary mechanism for delivering careers improvement and capacity-building support to schools, colleges, youth support services and CEIAG practitioners across West Yorkshire. |  | 2120000 | 1M-5M |  | Employment & Skills | Inclusive Economy, Skills & Culture
Sector Focused procurement | Sector focused training this might include telecoms and rail training as 25/26 is the last year we can extend these contracts, but the sectors will all be based on evidence of need. Potentially could be all levels, quals/non-reg and delivery models again all based one evidence of need. | N/A | 2400000 | 1M-5M | Learning & Development | Employment & Skills | Inclusive Economy, Skills & Culture
RVM Bus Fleet - Interim Branding Vinyls | Procuring a preferred supplier of high quality Weaver Network branding vinyl stickers. The procurement will allow franchise operators to purchase stickers directly from the supplier in order to meet franchise contract branding requirements. The CA will not purchase itself, rather mandate the purchasing by operators |  | 2550000 | 1M-5M
Leeds Bus Station Roof - Works | Leeds Bus Station Roof - Works |  | 6100000 | 5M-10M | Building | Facilities & Assets | Transport Services |  |  |  | 2027-06-01
Mass Transit - Business Case Consultancy Support | Mass Transit - Business Case Consultancy Support |  | 30000000 | 20M+ | Professional Services | Mass Transit | Mass Transit |  |  |  | 2027-01-31
Vehicles for Bus Franchising - Round Three | Procurement of buses for bus reform - round three |  | 270000000 | 20M+ | Fleet | Bus Reform | Bus Franchising
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please amend to 60 Characters or less when transferring from previous tab